## CDP PR Cover Sheet
For the attention of the Department for the Economy (DfE)
2021-22 College Development Plan - Progress Report
College: | Belfast Met
Period: | As at end of |  | 2022-07-01
Classification: | NON Confidential
Objective: | To provide DfE with an update on Belfast Met's performance against its College Development Plan 2021-22.
Reporting Officer: | Louise Warde Hunter
Background
In November 2021 DfE approved Belfast Met's College Development Plan (CDP) 2021-22 which serves as the baseline against which delivery of operational targets is to be measured throughout the academic year. The CDP Progress Report is used to update DfE on progress against: • Addressing any Residual Qualifications; and • Overall College Performance using the three CDP report cards: o 2021/22 Qualifications; o Employers; and o Social Inclusion.
The CDP Progress Report provides a reporting template for Colleges to report on progress against CDPs on a four monthly basis. The three reporting periods are as at the end of: • July • November • March A timetable can be seen below.
CDP Progress Report | Date of CDR Data Lift* |  | Date Return Due to DfE**
to DfE**
2021-11-01 | Tuesday 30 November 2021 |  | Friday 17 December 2021
2022-03-01 | Thursday 31 March 2022 |  | Friday 15 April 2022
2022-07-01 | Friday 29 July 2022 |  | Friday 12 August 2022
*Dates as per the CDR data lift scehdule.
**Dates as per the Returns Timetable for the year 01 August 2021 to 31 July 2022.
Progress reports take into account that the Employer activity is reported for the Departmental financial year (1st April – 31st March) and all other activity is reported for the College academic year (1st August - 31st July).
We have taken an Outcomes Based approach to setting our key priorities for 2021-22 based on the needs of the population in light of COVID-19 and aligning to the Programme for Government outcomes. Residual Qualifications along with the three report cards set out the planned activity for 2021/22 in-line with our approved 2021/22 CDP.
Our performance against the Residual Qualifications, Overall College Performance and the three report cards has been assessed against the following 4 level colour system (RAG status) to give an ‘at a glance indication’ of progress:
On Track / Achieved / Completed
Slippages / Areas Being Monitored
Not Likely to be Met / Not Met / Not Achieved
Not Yet Started / Reported or Data Not Yet Available
In-year performance is assessed against the full 4 RAG statuses above. Year-end performance is only assessed against ‘Completed’, ‘Not Achieved’ or ‘Reports or Data Not Yet Available’. It is noted that no tolerances have been applied towards achievement of planned activity and consideration should be given to the supporting narrative where under delivery has been reported.
Confirmation of the Accuracy and Reliability of the College Data Reported
Signed: |  |  |  | Date: | 2022-08-12
Principal / Chief Executive on behalf of the college

## Residual Progress Summary
Progress Against Residual Qualifications Included in 2021/22 CDPs
This section provides DfE with progress against planned enrolment activity as set out in the agreed 2021/22 CDP. Progress is assessed against the 4 level colour system. Where a yellow or red RAG status has been provided, reasons for the variance and actions taken / planned are provided.
2019/20 Residual Qualifications
Area of Planned Activity | 2021/22 Planned Activity | Completed in 2021/22 Academic Year | RAG Reason(s) for Variances and Actions Taken / Planned
FE Activity | 2 | 2
FT HE in FE | 0 | 0
PT HE in FE | 0 | 0
TfS | 0 | 0
AppsNI | 0 | 0
HLAs | 0 | 0
ES | 0 | 0
2020/21 Residual Qualifications
Area of Planned Activity | 2021/22 Planned Activity | Completed in 2021/22 Academic Year | RAG Reason(s) for Variances and Actions Taken / Planned
FE Activity | 8 | 8
FT HE in FE | 0 | 0
PT HE in FE | 0 | 0
TfS | 0 | 0
AppsNI | 22 | 22
HLAs | 0 | 0
ES | 0 | 0
NB: Breakdown of the Residual Qualifications Report Card can be found in the 'Residual Quals ' tab.

## Qualifications Progress Summary
Progress Against 2021/22 Qualifications
This section provides DfE with progress against planned activity as set out in the agreed 2021/22 CDP. Progress is measured against the No. of Individuals area of planned activity and assessed against the 4 level colour system. Where a yellow or red RAG status has been provided, reasons for the variance and actions taken / planned are provided.
2021/22 Qualifications (Academic Year)
Area of Planned Activity | 2021/22 Planned Activity |  | 2021/22 Activity Achieved |  | RAG & Reason(s) for Variances and Action(s) Taken / Planned
| No. of Enrols | No. of Individuals | No. of Enrols | No. of Individuals
FT FE Activity | 2791 | 2791 | 2864 | 2799
PT FE Activity | 11811 | 4564 | 12665 | 4795
FT HE in FE | 1487 | 1487 | 1092 | 1087 | As reported in December 2021, we had hoped that our Winter HE Campaign would help increase FT HE enrolments. In January 2022 however we confirmed with DfE that enrolments would not increase significantly as many applicants were unable to meet the entry criteria. As at the end of July 2022, this position remains unchanged.
PT HE in FE | 1096 | 953 | 1198 | 1038
TfS | 32 | 32 | 36 | 36
Skills for Life & Work | 100 | 100 | 0 | 0 | The College will deliver Skills for Life & Work from September 2022.
Traineeships | 134 | 134 | 145 | 104
AppsNI | 968 | 968 | 953 | 841 | There is a shortfall of 13 enrols therefore the College is within 2% of target.
% of AppsNI apprentices who remain on the programme for at least 4 weeks after initial registration and go on to remain on the programme for more than 52 weeks. | 82% |  |  |  | Performance against target cannot be assessed until September 2022.
HLAs | 229 | 229 | 218 | 206 | There is a shortfall of 11 enrols therefore the College is within 5% of target. A number of HLA enrols are in the Public Sector and have therefore been excluded from this heading and instead have been included under PT HE otherwise the target would have been met.
ES | 2100 | 1500 | 2212 | 1571
PSSA | 9627 | 5801 | 10815 | 6858
No. of Final Yr students enrolled in one+ PSSA subjects | 4750 |  | 6476
NB: Breakdown of the 2021/22 Qualification Report Card can be found in the '21-22 Quals' tab.

## Prison Service Delivery
Progress Against Prison Service Delivery Report Card
This section provides DfE with progress against planned activity as set out in the agreed 2021/22 CDP. Progress is assessed against the 4 level colour system. Where a yellow or red RAG status has been provided, reasons for the variance and actions taken / planned are provided.
Prison Service Delivery (Academic Year)
Area of Planned Activity | 2021/22 Planned Activity |  | 2021/22 Activity Achieved |  | RAG & Reason(s) for Variances and Action(s) Taken / Planned
| No. of Enrols | No. of Individuals | Enrols | No. of Individuals
Prisoners in Maghaberry Prison Undertaking College led courses | 347 | 347 | 359 | 272 | Enrols exceeded however variance for number of individuals due to shift in prison population e.g release, probation etc. Please note that numbers in the ERC do not reconcile with actual numbers reported as not all prison service delivery is currently captured in EBS.
Prisoners in Hydebank Prison Undertaking College led courses | 90 | 90 | 207 | 150 | Enrols exceeded however variance for number of individuals due to the shift in the prison population. Please note that numbers in the ERC do not reconcile with actual numbers reported as not all prison service delivery is currently captured in EBS.
Prisoners in Magilligan Prison Undertaking College led courses | 324 | 324 | 507 | 258 | Enrols exceeded however variance for number of individuals due to shift in prison population e.g release, probation etc. Please note that numbers in the ERC do not reconcile with actual numbers reported as not all prison service delivery is currently captured in EBS.

## Employers Progress Summary
Progress Against Employers Report Card
This section provides DfE with progress against planned activity as set out in the agreed 2021/22 CDP. Progress is assessed against the 4 level colour system. Where a yellow or red RAG status has been provided, reasons for the variance and actions taken / planned are provided.
Employers (2021/22 Financial Year)
Programme | Area of Planned Activity | 2021/22 Planned Activity | 2021/22 Activity Achieved | RAG & Reason(s) for Variances and Action(s) Taken / Planned
InnovateUs | No. of projects to be delivered through the InnovateUs programme | 69 | 78 projects completed
| Budget spend on projects completed | £300k | £300,200
Skills Focus | No. of enrolments undertaking a Level 2 (and above) qualifications through the Skills Focus Programme | 300 | 322
| Budget spend on projects completed | £350k | £350,069
Assured Skills Academies | No. of Academies to be delivered | 21 Academies with 320 enrolments equating to 320 individuals | 22 Academies with 374 enrolments delivered in the 21/22 financial year
Innovation Voucher Scheme | No. of vouchers | 13 | 17

## Social Inclusion Progress Summa
Progress Against Social Inclusion Report Card
This section provides DfE with progress against planned enrolment activity as set out in the agreed 2021/22 CDP. Progress is assessed against the 4 level colour system. Where a yellow or red RAG status has been provided, reasons for the variance and actions taken / planned are provided.
Social Inclusion (Academic Year)
Area of Planned Activity | 2021/22 Planned Activity | 2021/22 Activity Achieved | RAG & Reason(s) for Variances and Action(s) Taken / Planned
Enrolments within Quintile 1 and 2 | 7372 | 9488
Enrolments declaring a disability / long term health problem | 2065 | 2891
Enrolments on Entry Level and Level 1 Programmes (including Essential Skills) | 4238 | 5682
Enrolments on Targeted Programmes:
College Connect and Skills for Industry | 77 | 73 | Skills for Industry completed end of March 2022. College Connect as a six college consortium achieved their overall recruitment target for the year.
Futures | 45 | 137
Princes Trust | 42 | 29 | Lower numbers than anticipated due to extreme competition in North Belfast from similar internal and external community based programmes.
Skill UP | 605 | 528 | Some Academies with anticipated enrols were not delivered impacting on actual enrols in this programme.
Enrolments on ESOL Programmes | 1200 | 1739
Overall number of individuals supported by above measures | 6408 | 7670

## Notes
Guidance Notes
| Definitions | Notes
2021/22 Qualifications Summary | Excludes Residual Qualifications | FE01-0919 FE Coding Guidance - Course and Student Source of Funding (Addemdum 2)
Residual Qualifications | The purpose is to capture 'residual' enrolments who have returned to finish an enrolment that would normally have been completed, but was delayed by COVID-19 restrictions. | Circular FE08-21: Identification of COVID 19 Affected Enrolments
Individuals | Individuals are ranked as follows: 1. Full-time courses will take precedence over part-time. 2. Enrolments will be ranked by descending number of student hours. 3. Multiple enrolments with the same number of student hours will be ranked by descending level. 4. The highest ranking enrolment in the programme of study will then be designated as the primary enrolment, and the individual will therefore be defined as per the characteristics of this enrolment. 5. For Whole College, Essential Skills (ES) and PPSA tables, individual counts are calculated with a base population relevant to the respective table. E.g. for ES, only ES enrolments are considered and consideration is not given to any other courses those individuals are enrolled on outside the specified area. | As per approach agreed at workshop on 9 March 2020 - issued to colleges 16 March 2020.
Enrolments Excluded |  | Notes
All Funding Streams | Enrolments where the student has withdrawn before 1st November if Full-Time or has not completed 1/9 of their course if Part-Time (FEI_1 = 0) Enrolments with a student status of '4' - (Transferred)
Funding Streams | Student Source of Funding | NVQ Level
Mainstream | 07, 18, 96 (Advanced Technical Award) & 99 | 0,1 2,3,9 OR Blank
Cost Recovery | 45, 46, 58, 59 & 80 (NI Prison Service Provision)
Employer Led Activity | 48: Bridge To Employment Programme
49: Business Improvements Techniques Programme
52: Assured Skills Programme
62: InnovateUs
63: Skills Focus Programme
FE Entitlement Framework | 02 & 20
Other | 54
60 & 98
70: Skills Intervention
71: Skill Up - Flexible Skills Fund
Total FE | As per Above
Total HE in FE | All codes excluding (Government Training Programmes) | 4,5 6,7,8
Government Training Programmes | 42 - Skills for Life and Work (from 2021/22) | 0,1 2,3,9 OR Blank
43 - Tfs: Skills for Your Life, 44 - Tfs: Skills for Work
51: ApprenticeshipsNI
66 & 69: HLAs
| 97: Traineeships | 4,5 6,7,8
Mode of Attendance | Student Mode of Attendance | Notes
FT | '01 - Full-time >=30 Wks and 20 - Combined Full-time (Primary)
PT | All codes excluding ( 01 & 20)
GCSE/A-Level | Qualification Aim
GCSE/A-Level Enrolments | 560 - GCSE, 614 - AS Level & 615 - A2 Level
Regulated Status | Regulated Indicator
Non - Regulated | 0
Essential Skills Age Groups | Essential Skills Indicator | Age Parameters
Under 16 | 1 | <16
16-19 | 1 | >=16 AND <=19
20+ | 1 | >= 20

## Prog. Report ERC - 21-22 Quals
2021/22 WHOLE COLLEGE ACTIVITY - PROGRESS REPORT (Excluding Residual Qualifications)
INSERT COLLEGE LOGO HERE
ENROLMENT ACTIVITY (EXCLUDING ESSENTIAL SKILLS) |  | 2021/22 Planned Activity |  |  | 2021/22 Activity Achieved |  |  | % of 2021/22 Planned Activity Achieved |  |  | Level 0 |  | Level 1 |  | Level 2 |  | Level 3 |  | Level 4 |  | Level 5 |  | Level 6 |  | Level 7+ |  | Planned % of Overall College Provision | Actual % of Overall College Provision
|  | Enrolments |  |  | Enrolments |  |  | Enrolments |  |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments | Enrolments
|  | PT | FT | Total | PT | FT | Total | PT | FT | Total | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | FT & PT | FT & PT
FE MAINSTREAM: 7, 18, 96 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  | 8778 | 2791 | 11569 | 9494 | 2746 | 12240 | 108.2% | 98.39% | 105.8% | 1779 | 94 | 523 | 121 | 4706 | 516 | 2486 | 2015 | [8 empty] | 62.04% | 63.85%
HE MAINSTREAM: 7, 18 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  | 773 | 1487 | 2260 | 835 | 1087 | 1922 | 108% | 73.1% | 85.04% | [8 empty] | 398 | 51 | 319 | 918 | 118 | 118 |  |  | 12.12% | 10.03%
FE & HE COST RECOVERY | 45, 46, 58 & 59 | 1175 | 0 | 1175 | 1761 | 98 | 1859 | 149.9% | 0% | 158.2% | 1005 |  | 34 |  | 379 | 9 | 123 | 84 | 189 |  | 18 | 5 | 2 |  | 11 |  | 6.301% | 9.697%
| 80 - NI Prison Service Provision | 437 | 0 | 437 | 54 | 0 | 54 | 12.36% | 0% | 12.36% | 53 |  |  |  | 1 | [11 empty] | 2.343% | 0.2817%
FE & HE EMPLOYER LED ACTIVITY - Financial Yr | 48: Bridge to Employment | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [16 empty] | 0% | 0%
| 49: Business Improvements Techniques Programme | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [16 empty] | 0% | 0%
| 52: Assured Skills | 400 | 0 | 400 | 386 | 0 | 386 | 96.5% | 0% | 96.5% | 386 | [15 empty] | 2.145% | 2.013%
| 62: InnovateUs | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [16 empty] | 0% | 0%
| 63: Skills Focus | 300 | 0 | 300 | 278 | 3 | 281 | 92.67% | 0% | 93.67% | 4 |  |  |  | 76 |  | 91 | 3 | 37 |  | 39 |  | 29 |  | 2 |  | 1.609% | 1.466%
FE ENTITLEMENT FRAMEWORK |  | 317 | 0 | 317 | 293 | 8 | 301 | 92.43% | 0% | 94.95% | 82 |  | 17 |  | 14 |  | 180 | 8 | [8 empty] | 1.7% | 1.57%
FE & HE OTHER | 54: ESF | 77 | 0 | 77 | 67 | 14 | 81 | 87.01% | 0% | 105.2% | 21 |  | 36 | 14 | 10 | [11 empty] | 0.4129% | 0.4225%
| 60 & 98 | 45 | 0 | 45 | 167 | 0 | 167 | 371.1% | 0% | 371.1% | 98 |  |  |  | 67 |  | 2 | [9 empty] | 0.2413% | 0.8711%
| 70: Skills Intervention | 0 | 0 | 0 | 37 | 0 | 37 | 0% | 0% | 0% |  |  |  |  | 24 |  | 13 | [9 empty] | 0% | 0.193%
| 71: Skill Up - Flexible Skills Fund | 605 | 0 | 605 | 491 | 0 | 491 | 81.16% | 0% | 81.16% | 29 |  |  |  | 275 |  | 151 |  | 14 |  | 22 | [5 empty] | 3.244% | 2.561%
TOTAL FE |  | 11811 | 2791 | 14602 | 12665 | 2864 | 15529 | 107.2% | 102.6% | 106.3% | 3457 | 94 | 610 | 135 | 5552 | 525 | 3046 | 2110 | [8 empty] | 78.3% | 81%
TOTAL HE in FE |  | 1096 | 1487 | 2583 | 1198 | 1092 | 2290 | 109.3% | 73.44% | 88.66% | [8 empty] | 638 | 51 | 398 | 923 | 149 | 118 | 13 | 0 | 13.85% | 11.95%
GOVMT TRAINING PROGRAMMES | Non - Employed
| 43 & 44 - TfS (L0-3) | 0 | 32 | 32 | 0 | 36 | 36 | 0% | 112.5% | 112.5% | [5 empty] | 36 | [10 empty] | 0.1716% | 0.1878%
| 42 - Skills for Life and Work (L0-2) | 0 | 100 | 100 | 0 | 0 | 0 | 0% | 0% | 0% | [16 empty] | 0.5363% | 0%
| 97 - Traineeships (L2) | 0 | 134 | 134 | 35 | 110 | 145 | 0% | 82.09% | 108.2% |  |  |  |  | 35 | 110 | [10 empty] | 0.7186% | 0.7564%
Employed
| 51: AppsNI (L2 & 3) | 410 | 558 | 968 | 116 | 837 | 953 | 28.29% | 150% | 98.45% |  |  |  |  | 76 | 197 | 40 | 640 | [8 empty] | 5.191% | 4.971%
| 66 & 69: HLA (L4 & 5) | 229 | 0 | 229 | 218 | 0 | 218 | 95.2% | 0% | 95.2% | [8 empty] | 11 |  | 198 |  | 9 |  |  |  | 1.228% | 1.137%
TOTAL REGULATED AND NON-REGULATED ENROLMENTS |  | 13546 | 5102 | 18648 | 14232 | 4939 | 19171 | 105.1% | 96.81% | 102.8% | 3457 | 94 | 610 | 135 | 5663 | 868 | 3086 | 2750 | 649 | 51 | 596 | 923 | 158 | 118 | 13 | 0
NON-REGULATED ONLY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
INDIVIDUAL ACTIVITY (EXCLUDING ESSENTIAL SKILLS) |  | 2021/22 Planned Activity |  |  | 2021/22 Activity Achieved |  |  | % of 2021/22 Planned Activity Achieved |  |  | Level 0 |  | Level 1 |  | Level 2 |  | Level 3 |  | Level 4 |  | Level 5 |  | Level 6 |  | Level 7+ |  | Planned % of Overall College Provision | Actual % of Overall College Provision
|  | Individuals |  |  | Individuals |  |  | Individuals |  |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals | Individuals
|  | PT | FT | Total | PT | FT | Total | PT | FT | Total | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | FT & PT | FT & PT
FE MAINSTREAM: 7, 18. 96 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  | 2017 | 2791 | 4808 | 2328 | 2687 | 5015 | 115.4% | 96.27% | 104.3% | 685 | 93 | 108 | 116 | 729 | 503 | 806 | 1975 | [8 empty] | 25.78% | 26.16%
HE MAINSTREAM: 7, 18 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  | 664 | 1487 | 2151 | 705 | 1082 | 1787 | 106.2% | 72.76% | 83.08% | [8 empty] | 314 | 51 | 288 | 913 | 103 | 118 |  |  | 11.53% | 9.321%
FE & HE COST RECOVERY | 45, 46, 58 & 59 | 755 | 0 | 755 | 1355 | 93 | 1448 | 179.5% | 0% | 191.8% | 715 |  | 13 |  | 319 | 8 | 88 | 80 | 189 |  | 18 | 5 | 2 |  | 11 |  | 4.049% | 7.553%
| 80 - NI Prison Service Provision | 437 | 0 | 437 | 38 | 0 | 38 | 8.696% | 0% | 8.696% | 38 | [15 empty] | 2.343% | 0.1982%
FE & HE EMPLOYER LED ACTIVITY - Financial Yr | 48: Bridge to Employment | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [16 empty] | 0% | 0%
| 49: Business Improvements Techniques Programme | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [16 empty] | 0% | 0%
| 52: Assured Skills | 400 | 0 | 400 | 379 | 0 | 379 | 94.75% | 0% | 94.75% | 379 | [15 empty] | 2.145% | 1.977%
| 62: InnovateUs | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [16 empty] | 0% | 0%
| 63: Skills Focus | 260 | 0 | 260 | 236 | 3 | 239 | 90.77% | 0% | 91.92% | 1 |  |  |  | 69 |  | 89 | 3 | 20 |  | 38 |  | 17 |  | 2 |  | 1.394% | 1.247%
FE ENTITLEMENT FRAMEWORK |  | 257 | 0 | 257 | 239 | 8 | 247 | 93% | 0% | 96.11% | 45 |  | 3 |  | 14 |  | 177 | 8 | [8 empty] | 1.378% | 1.288%
FE & HE OTHER | 54: ESF | 77 | 0 | 77 | 29 | 13 | 42 | 37.66% | 0% | 54.55% | 6 |  | 23 | 13 | [12 empty] | 0.4129% | 0.2191%
| 60 & 98 | 45 | 0 | 45 | 99 | 0 | 99 | 220% | 0% | 220% | 59 |  |  |  | 38 |  | 2 | [9 empty] | 0.2413% | 0.5164%
| 70: Skills Intervention | 0 | 0 | 0 | 26 | 0 | 26 | 0% | 0% | 0% |  |  |  |  | 13 |  | 13 | [9 empty] | 0% | 0.1356%
| 71: Skill Up - Flexible Skills Fund | 605 | 0 | 605 | 399 | 0 | 399 | 65.95% | 0% | 65.95% | 26 |  |  |  | 210 |  | 127 |  | 14 |  | 22 | [5 empty] | 3.244% | 2.081%
TOTAL FE |  | 4564 | 2791 | 7355 | 4795 | 2799 | 7594 | 105.1% | 100.3% | 103.2% | 1954 | 93 | 147 | 129 | 1392 | 511 | 1302 | 2066 | [8 empty] | 39.44% | 39.61%
TOTAL HE in FE |  | 953 | 1487 | 2440 | 1038 | 1087 | 2125 | 108.9% | 73.1% | 87.09% | [8 empty] | 537 | 51 | 366 | 918 | 122 | 118 | 13 | 0 | 13.08% | 11.08%
GOVMT TRAINING PROGRAMMES | Non - Employed
| 43 & 44 - TfS (L0-3) | 0 | 32 | 32 | 0 | 36 | 36 | 0% | 112.5% | 112.5% | [5 empty] | 36 | [10 empty] | 0.1716% | 0.1878%
| 42 - Skills for Life and Work (L0-2) | 0 | 100 | 100 | 0 | 0 | 0 | 0% | 0% | 0% | [16 empty] | 0.5363% | 0%
| 97 - Traineeships (L2) | 0 | 134 | 134 | 1 | 103 | 104 | 0% | 76.87% | 77.61% |  |  |  |  | 1 | 103 | [10 empty] | 0.7186% | 0.5425%
Employed
| 51: AppsNI (L2 & 3) | 410 | 558 | 968 | 21 | 820 | 841 | 5.122% | 147% | 86.88% |  |  |  |  | 10 | 187 | 11 | 633 | [8 empty] | 5.191% | 4.387%
| 66 & 69: HLA (L4 & 5) | 229 | 0 | 229 | 206 | 0 | 206 | 89.96% | 0% | 89.96% | [8 empty] | 11 |  | 188 |  | 7 |  |  |  | 1.228% | 1.075%
TOTAL REGULATED AND NON-REGULATED ENROLMENTS |  | 6156 | 5102 | 11258 | 6061 | 4845 | 10906 | 98.46% | 94.96% | 96.87% | 1954 | 93 | 147 | 129 | 1403 | 837 | 1313 | 2699 | 548 | 51 | 554 | 918 | 129 | 118 | 13 | 0
NON-REGULATED ONLY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Essential Skills
Programme |  |  |  |  | TfS Enrols | [8 empty] | FE Enrols | [8 empty] | AppsNI Enrols | [8 empty] | Traineeships Enrols |  |  | Skills for Life and Work Enrols | [8 empty] | 2021/22 Planned Enrolments |  |  |  | 2021/22 Enrolments Achieved |  |  |  | % of 2021/22 Planned Enrolments Achieved |  |  |  | No. of individuals enrolled on any ES courses
Level |  |  |  |  | EL |  |  | L1 |  |  | L2 |  |  | EL |  |  | L1 |  |  | L2 |  |  | EL |  |  | L1 |  |  | L2 |  |  | L2 |  |  | EL |  |  | L1 |  |  | L2 | [14 empty] | 2021/22 Planned Activity | 2021/22 Activity Achieved | % of 2021/22 Planned Activity Achieved
[5 empty] | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Total | Lit | Num | ICT | Total | Lit | Num | ICT | Total | 1500 | 1571 | 104.7%
Age under 16 | 2021/22 Planned Activity |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 5 | 0% | 0% | 0% | 0%
| 2021/22 Activity Achieved | [13 empty] | 1 |  |  |  |  | 2 | 2
>=16 and <20 | 2021/22 Planned Activity |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 120 | 0 | 130 | 240 | 140 | 130 | 190 | 70 | 0 | 0 | 0 | 3 | 3 | 4 | 3 | 3 | 4 | 35 | 35 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391 | 591 | 258 | 1240 | 377 | 449 | 236 | 1062 | 96.42% | 75.97% | 91.47% | 85.65%
| 2021/22 Activity Achieved | [6 empty] | 6 | 4 | 9 | 4 | 1 | 6 | 97 | 149 |  | 128 | 169 | 97 | 103 | 78 | 32 | 2 | 3 |  | 4 | 6 | 56 | 3 | 1 | 11 | 30 | 38 | 25
Age 20 and over | 2021/22 Planned Activity |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 70 | 0 | 40 | 80 | 100 | 160 | 200 | 70 | 0 | 0 | 0 | 3 | 3 | 4 | 3 | 3 | 4 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 366 | 188 | 860 | 430 | 517 | 198 | 1145 | 140.5% | 141.3% | 105.3% | 133.1%
| 2021/22 Activity Achieved |  |  |  | 2 |  |  | 5 | 1 |  | 1 |  |  | 129 | 101 |  | 113 | 155 | 126 | 177 | 250 | 59 |  |  |  |  | 2 | 12 |  | 3 |  | 3 | 5 | 1
[44 empty] | 697 | 957 | 446 | 2100 | 809 | 969 | 434 | 2212 | 116.1% | 101.3% | 97.31% | 105.3%
Programme Totals | 2021/22 Planned Activity |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 370 |  |  | 730 |  |  | 820 |  |  | 0 |  |  | 20 |  |  | 20 |  |  | 140 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | EL | L1 | l2 |  | EL | L1 | L2 |  | EL | L1 | L2
| 2021/22 Activity Achieved |  |  |  | 2 |  |  | 25 |  |  | 12 |  |  | 477 |  |  | 788 |  |  | 703 |  |  | 5 |  |  | 80 |  |  | 18 |  |  | 102 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 370 | 750 | 980 |  | 484 | 893 | 835 |  | 130.8% | 119.1% | 85.2%
GCSEs
Programme |  |  |  |  | TFS | FE | AppsNI | Trainee-ships | Skills for Life and Work | 2021/22 Planned Activity | 2021/22 Activity Achieved | % of 2021/22 Planned Activity Achieved
Enrols | PT | 2021/22 Planned Activity |  |  | 0 | 392 | 0 | 0 | 0 | 392 | 537 | 137%
|  | 2021/22 Activity Achieved |  |  |  | 537
| FT | 2021/22 Planned Activity |  |  | 0 | 35 | 0 | 0 | 0 | 35 | 33 | 94.29%
|  | 2021/22 Activity Achieved |  |  |  | 33
Total enrolments | [9 empty] | 427 | 570 | 133.5%
A Level
Programme |  |  |  |  | TFS (43 & 44) | FE | AppsNI (51) | Traineeships (TBD) | Skills for Life and Work | 2021/22 Planned Activity | 2021/22 Activity Achieved | % of 2021/22 Planned Activity Achieved
Enrols | PT | 2021/22 Planned Activity |  |  | 0 | 1176 | 0 | 0 | 0 | 1176 | 1410 | 119.9%
|  | 2021/22 Activity Achieved |  |  |  | 1410
| FT | 2021/22 Planned Activity |  |  | 0 | 381 | 0 | 0 | 0 | 381 | 392 | 102.9%
|  | 2021/22 Activity Achieved |  |  |  | 392
Total enrolments | [9 empty] | 1557 | 1802 | 115.7%

## Prog. Report ERC - Resid Quals
RESIDUAL QUALIFICATIONS - PROGRESS REPORT
INSERT COLLEGE LOGO HERE
2019/20 RESIDUAL ENROLMENT ACTIVITY (EXCLUDING ESSENTIAL SKILLS) |  | 2019/20 enrolments planned to be completed in 2021/22 academic year |  |  | 2019/20 enrolment activity completed in 2021/22 Academic Year |  |  | % of 2019/20 residual activity completed in 2021/22 academic year | Level 0 |  | Level 1 |  | Level 2 |  | Level 3 |  | Level 4 |  | Level 5 |  | Level 6 |  | Level 7+
|  | Enrolments |  |  | Enrolments |  |  |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments
|  | PT | FT | Total | PT | FT | Total |  | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT
FE MAINSTREAM: 7, 18, 96 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  | 2 | 0 | 2 | 2 | 0 | 2 | 100 |  |  |  |  | 1 |  | 1
HE MAINSTREAM: 7, 18 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE & HE COST RECOVERY | 45, 46, 58 & 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80 - NI Prison Service | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE & HE EMPLOYER LED ACTIVITY - Financial Yr | 48: Bridge to Employment | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 49: Business Improvements Techniques Programme | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 52: Assured Skills | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 62: InnovateUs | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 63: Skills Focus | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE ENTITLEMENT FRAMEWORK |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE & HE OTHER | 54: ESF | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 60 & 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 70: Skills Intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 71: Skill Up - Flexible Skills Fund | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL FE |  | 2 | 0 | 2 | 2 | 0 | 2 | 100 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
TOTAL HE in FE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GOVMT TRAINING PROGRAMMES | Non - Employed
| 43 & 44 - TfS (L0-3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 42 - Skills for Life and Work (L0-2) | N/A | N/A | N/A | 0 | 0 | 0 | N/A
| 97 - Traineeships (L2) | N/A | N/A | N/A | 0 | 0 | 0 | N/A
Employed
| 51: AppsNI (L2 & 3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66 & 69: HLA (L4 & 5) | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL REGULATED AND NON-REGULATED ENROLMENTS |  | 2 | 0 | 2 | 2 | 0 | 2 | 100 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020/21 RESIDUAL ENROLMENT ACTIVITY (EXCLUDING ESSENTIAL SKILLS) |  | 2020/21 enrolments planned to be completed in 2021/22 academic year |  |  | 2020/21 enrolment activity completed in 2021/22 Academic Year |  |  | % of 2020/21 residual activity completed in 2021/22 academic year | Level 0 |  | Level 1 |  | Level 2 |  | Level 3 |  | Level 4 |  | Level 5 |  | Level 6 |  | Level 7+
|  | Enrolments |  |  | Enrolments |  |  |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments
|  | PT | FT | Total | PT | FT | Total |  | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT
FE MAINSTREAM: 7, 18, 96 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  | 0 | 8 | 8 | 0 | 8 | 8 | 100 | [5 empty] | 6 |  | 2
HE MAINSTREAM: 7, 18 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE & HE COST RECOVERY | 45, 46, 58 & 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80 - NI Prison Service | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE & HE EMPLOYER LED ACTIVITY - Financial Yr | 48: Bridge to Employment | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 49: Business Improvements Techniques Programme | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 52: Assured Skills | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 62: InnovateUs | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 63: Skills Focus | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE ENTITLEMENT FRAMEWORK |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE & HE OTHER | 54: ESF | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 60 & 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 70: Skills Intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 71: Skill Up - Flexible Skills Fund | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL FE |  | 0 | 8 | 8 | 0 | 8 | 8 | 100 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 2
TOTAL HE in FE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GOVMT TRAINING PROGRAMMES | Non - Employed
| 43 & 44 - TfS (L0-3) | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 42 - Skills for Life and Work (L0-2) | N/A | N/A | N/A | 0 | 0 | 0 | N/A
| 97 - Traineeships (L2) | N/A | N/A | N/A | 0 | 0 | 0 | N/A
Employed
| 51: AppsNI (L2 & 3) | 12 | 10 | 22 | 12 | 10 | 22 | 100 | [6 empty] | 12 | 10
| 66 & 69: HLA (L4 & 5) | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL REGULATED AND NON-REGULATED ENROLMENTS |  | 12 | 18 | 30 | 12 | 18 | 30 | 100 | 0 | 0 | 0 | 0 | 0 | 6 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Essential Skills
Level |  |  |  |  | EL | L1 | L2 | Total Residual Planned Activity | 2021/22 Total Residual Activity Achieved | % of 2021/22 Planned Residual Activity Achieved
2019/20 Residual enrolments planned to be completed in 2021/22 academic year |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0%
2019/20 Residual enrolments completed in 2021/22
2020/21 Residual enrolments planned to be completed in 2021/22 academic year |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0%
2020/21 Residual enrolments completed in 2021/22
Total | [7 empty] | 0 | 0 | 0%

## Prog. Report ERC - PSSA
2021/22 Priority Sector Areas & STEM
Enrolment Activity
Priority Sector Areas and / or 'BROAD' STEM Planned Activity | Agri-Foods (including STEM) |  | Advanced Manufacturing Materials and Engineering (including STEM) |  | Construction and Materials Handling (including STEM) |  | Digital and Creative Technologies (including STEM) |  | Finance Business and Professional Services (including STEM) |  | Life and Health Sciences (including STEM) |  | TOTAL PRIORITY SECTOR AREAS ACHIEVED |  | STEM ACHIEVED (not already included in Priority Sector Areas) |  | 2021/22 TOTAL PLANNED PSSA ACTIVITY |  | 2021/22 TOTAL PSSA ACHIEVED |  | % OF 2021/22 PLANNED PSSA ACTIVITY ACHIEVED
| PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT
L0-1 |  |  | 10 | 15 | 45 | 14 | 297 |  | 775 |  |  |  | 1127 | 29 | 93 |  | 1053 | 28 | 1220 | 29 | 115.9% | 103.6%
L2 | 495 |  | 141 | 137 |  | 158 | 350 | 207 | 2000 | 133 | 73 | 38 | 3059 | 673 | 37 |  | 2998 | 521 | 3096 | 673 | 103.3% | 129.2%
L3 | 8 |  | 391 | 390 | 73 | 176 | 179 | 309 | 1026 | 688 | 329 | 125 | 2006 | 1688 | 134 | 39 | 1970 | 1262 | 2140 | 1727 | 108.6% | 136.8%
L4 + |  |  | 246 | 70 | 49 | 73 | 13 | 132 | 828 | 452 |  | 67 | 1136 | 794 |  |  | 1033 | 762 | 1136 | 794 | 110% | 104.2%
Totals | 503 | 0 | 788 | 612 | 167 | 421 | 839 | 648 | 4629 | 1273 | 402 | 230 | 7328 | 3184 | 264 | 39 | 7054 | 2573 | 7592 | 3223 | 107.6% | 125.3%
| 503 |  | 1400 |  | 588 |  | 1487 |  | 5902 |  | 632 |  | 10512 |  | 303 |  | 9627 |  | 10815
% Planned Provision | 1.678% |  | 7.706% |  | 3.314% |  | 6.875% |  | 28.84% |  | 2.831% |  | 51.25% |  | 0.3754% |  | 51.62%
% Provision Achieved | 2.624% |  | 7.303% |  | 3.067% |  | 7.757% |  | 30.79% |  | 3.297% |  | 54.83% |  | 1.581% |  | 50.22%
Individual Activity
Priority Sector Areas and / or 'BROAD' STEM Planned Activity | Agri-Foods (including STEM) |  | Advanced Manufacturing Materials and Engineering (including STEM) |  | Construction and Materials Handling (including STEM) |  | Digital and Creative Technologies (including STEM) |  | Finance Business and Professional Services (including STEM) |  | Life and Health Sciences (including STEM) |  | TOTAL PRIORITY SECTOR AREAS ACHIEVED |  | STEM ACHIEVED (not already included in Priority Sector Areas) |  | 2021/22 TOTAL PLANNED PSSA ACTIVITY |  | 2021/22 TOTAL PSSA ACHIEVED |  | % OF 2021/22 PLANNED PSSA ACTIVITY ACHIEVED
| PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT
L0-1 |  |  | 6 | 15 | 40 | 14 | 225 |  | 589 |  |  |  | 860 | 29 | 48 |  | 109 | 28 | 908 | 29 | 833% | 103.6%
L2 | 299 |  | 87 | 136 |  | 146 | 59 | 200 | 271 | 130 | 23 | 38 | 739 | 650 | 4 |  | 551 | 521 | 743 | 650 | 134.8% | 124.8%
L3 | 8 |  | 189 | 382 | 18 | 173 | 86 | 300 | 454 | 679 | 185 | 118 | 940 | 1652 | 131 | 38 | 1442 | 1262 | 1071 | 1690 | 74.27% | 133.9%
L4 + |  |  | 245 | 70 | 49 | 73 | 4 | 131 | 680 | 448 |  | 67 | 978 | 789 |  |  | 1126 | 762 | 978 | 789 | 86.86% | 103.5%
Totals | 307 | 0 | 527 | 603 | 107 | 406 | 374 | 631 | 1994 | 1257 | 208 | 223 | 3517 | 3120 | 183 | 38 | 3228 | 2573 | 3700 | 3158 | 114.6% | 122.7%
| 307 |  | 1130 |  | 513 |  | 1005 |  | 3251 |  | 431 |  | 6637 |  | 221 |  | 5801 |  | 6858
% Planned Provision | 0.4885% |  | 9.753% |  | 5.028% |  | 5.436% |  | 26.52% |  | 3.677% |  | 50.91% |  | 34500% |  | 51.53%
% Provision Achieved | 2.815% |  | 10.36% |  | 4.704% |  | 9.215% |  | 29.81% |  | 3.952% |  | 60.86% |  | 2.026% |  | 53.19%
|  |  |  | PT | FT | Total
2021/22 Planned No, of Enrolments (excluding ES) |  |  |  | 13546 | 5102 | 18648
2021/22 Achieved No. of Enrolments (excluding ES) |  |  |  | 14232 | 4939 | 19171
2021/22 Planned No of Individuals (excluding ES) |  |  |  | 6156 | 5102 | 11258
2021/22 Achieved No. of Individuals (excluding ES) |  |  |  | 6061 | 4845 | 10906

## 2021-22 ERC
2021/22 WHOLE COLLEGE ACTIVITY (Excluding Residual Qualifications)
ENROLMENT ACTIVITY (EXCLUDING ESSENTIAL SKILLS) |  | 2020/21 In-Year Activity |  |  | 2021/22 Planned Activity |  |  | % of 2020/21 In-Year Activity |  |  | Level 0 |  | Level 1 |  | Level 2 |  | Level 3 |  | Level 4 |  | Level 5 |  | Level 6 |  | Level 7+ |  | 2020/21 % of Overall College Provision | 2021/22 Planned % of Overall College Provision
|  | Enrolments |  |  | Enrolments |  |  | Enrolments |  |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments | Enrolments
|  | PT | FT | Total | PT | FT | Total | PT | FT | Total | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | FT & PT | FT & PT
FE MAINSTREAM: 7, 18, 96 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  | 8750 | 2985 | 11735 | 8778 | 2791 | 11569 | 100.3% | 93.5% | 98.59% | 1515 | 87 | 491 | 125 | 4499 | 543 | 2273 | 2036 | [8 empty] | 63.5561 | 62.0388
HE MAINSTREAM: 7, 18 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  | 796 | 1260 | 2056 | 773 | 1487 | 2260 | 97.11% | 118% | 109.9% | [8 empty] | 329 | 64 | 330 | 1294 | 114 | 129 |  |  | 11.1352 | 12.1193
FE & HE COST RECOVERY | 45, 46, 58 & 59 | 926 | 53 | 979 | 1175 | 0 | 1175 | 126.9% | 0% | 120% | 800 |  | 33 |  | 84 |  | 106 |  | 129 |  | 4 |  |  |  | 19 |  | 5.3022 | 6.3009
| 80 - NI Prison Service Provision | 0 | 0 | 0 | 437 | 0 | 437 | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 263 |  | 174 | [11 empty] | 0 | 2.3434
FE & HE EMPLOYER LED ACTIVITY - Financial Yr | 48: Bridge to Employment | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | [16 empty] | 0 | 0
| 49: Business Improvements Techniques Programme | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | [16 empty] | 0 | 0
| 52: Assured Skills | 382 | 0 | 382 | 400 | 0 | 400 | 104.7% | #DIV/0! | 104.7% | 400 | [15 empty] | 2.0689 | 2.145
| 62: InnovateUs |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | [16 empty] | 0 | 0
| 63: Skills Focus | 233 | 2 | 235 | 300 | 0 | 300 | 128.8% | 0% | 127.7% |  |  |  |  | 118 |  | 71 |  | 50 |  | 50 |  | 11 |  |  |  | 1.2727 | 1.6088
FE ENTITLEMENT FRAMEWORK |  | 336 | 0 | 336 | 317 | 0 | 317 | 94.35% | #DIV/0! | 94.35% | 71 |  | 18 |  | 18 |  | 210 | [9 empty] | 1.8198 | 1.6999
FE & HE OTHER | 54: ESF | 115 | 18 | 133 | 77 | 0 | 77 | 66.96% | 0% | 57.89% |  |  | 77 | [13 empty] | 0.72032 | 0.41291
| 60 & 98 | 596 |  | 596 | 45 | 0 | 45 | 7.55% | #DIV/0! | 7.55% |  |  |  |  | 45 | [11 empty] | 3.2279 | 0.24131
| 70: Skills Intervention | 697 |  | 697 | 0 | 0 | 0 | 0% | #DIV/0! | 0% | [16 empty] | 3.7749 | 0
| 71: Skill Up - Flexible Skills Fund |  |  | 0 | 605 | 0 | 605 | #DIV/0! | #DIV/0! | #DIV/0! | 35 |  |  |  | 345 |  | 165 |  | 20 |  | 20 |  | 20 |  |  |  | 0 | 3.2443
TOTAL FE |  | 11736 | 3058 | 14794 | 11811 | 2791 | 14602 | 100.6% | 91.27% | 98.7% | 2821 | 87 | 882 | 125 | 5283 | 543 | 2825 | 2036 | [8 empty] | 80.1235 | 78.3033
TOTAL HE in FE |  | 1095 | 1260 | 2355 | 1096 | 1487 | 2583 | 100.1% | 118% | 109.7% | [8 empty] | 528 | 64 | 404 | 1294 | 145 | 129 | 19 | 0 | 12.7545 | 13.8514
GOVMT TRAINING PROGRAMMES | Non - Employed
| 43 & 44 - TfS (L0-3) | 0 | 159 | 159 | 0 | 32 | 32 | #DIV/0! | 20.13% | 20.13% | [5 empty] | 32 | [10 empty] | 0.86114 | 0.1716
| 42 - Skills for Life and Work (L0-2) | N/A | N/A | N/A | 0 | 100 | 100 | N/A | N/A | N/A |  |  |  | 100 | [12 empty] | N/A | 0.53625
| 97 - Traineeships (L2) | N/A | N/A | N/A | 0 | 134 | 134 | N/A | N/A | N/A | [5 empty] | 134 | [10 empty] | N/A | 0.71858
Employed
| 51: AppsNI (L2 & 3) | 572 | 403 | 975 | 410 | 558 | 968 | 71.68% | 138.5% | 99.28% |  |  |  |  | 70 | 148 | 340 | 410 | [8 empty] | 5.2805 | 5.1909
| 66 & 69: HLA (L4 & 5) | 181 | 0 | 181 | 229 | 0 | 229 | 126.5% | #DIV/0! | 126.5% | [8 empty] | 10 |  | 219 | [5 empty] | 0.98029 | 1.228
TOTAL REGULATED AND NON-REGULATED ENROLMENTS |  | 13584 | 4880 | 18464 | 13546 | 5102 | 18648 | 99.72% | 104.5% | 101% | 2821 | 87 | 882 | 225 | 5353 | 857 | 3165 | 2446 | 538 | 64 | 623 | 1294 | 145 | 129 | 19 | 0
NON-REGULATED ONLY |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
INDIVIDUAL ACTIVITY (EXCLUDING ESSENTIAL SKILLS) |  | 2020/21 In-Year Activity |  |  | 2021/22 Planned Activity |  |  | % of 2020/21 In-Year Activity |  |  | Level 0 |  | Level 1 |  | Level 2 |  | Level 3 |  | Level 4 |  | Level 5 |  | Level 6 |  | Level 7+ |  | 2020/21 % of Overall College Provision | 2021/22 Planned % of Overall College Provision
|  | Individuals |  |  | Individuals |  |  | Individuals |  |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals | Individuals
|  | PT | FT | Total | PT | FT | Total | PT | FT | Total | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | FT & PT | FT & PT
FE MAINSTREAM: 7, 18. 96 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  | 2172 | 2985 | 5157 | 2017 | 2791 | 4808 | 92.86% | 93.5% | 93.23% | 546 | 87 | 158 | 125 | 540 | 543 | 773 | 2036 | [8 empty] | 50.8329 | 42.7074
HE MAINSTREAM: 7, 18 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  | 668 | 1260 | 1928 | 664 | 1487 | 2151 | 99.4% | 118% | 111.6% | [8 empty] | 274 | 64 | 291 | 1294 | 89 | 129 | 10 |  | 19.0044 | 19.1064
FE & HE COST RECOVERY | 45, 46, 58 & 59 | 635 | 53 | 688 | 755 | 0 | 755 | 118.9% | 0% | 109.7% | 464 |  | 6 |  | 48 |  | 88 |  | 128 |  | 4 |  |  |  | 17 |  | 6.7817 | 6.7063
| 80 - NI Prison Service Provision |  | 0 | 0 | 437 | 0 | 437 | #DIV/0! | #DIV/0! | #DIV/0! |  |  | 263 |  | 174 | [11 empty] | 0 | 3.8817
FE & HE EMPLOYER LED ACTIVITY - Financial Yr | 48: Bridge to Employment |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | [16 empty] | 0 | 0
| 49: Business Improvements Techniques Programme |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | [16 empty] | 0 | 0
| 52: Assured Skills | 376 | 0 | 376 | 400 | 0 | 400 | 106.4% | #DIV/0! | 106.4% | 400 | [15 empty] | 3.7063 | 3.553
| 62: InnovateUs |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | [16 empty] | 0 | 0
| 63: Skills Focus | 199 | 2 | 201 | 260 | 0 | 260 | 130.7% | 0% | 129.4% |  |  |  |  | 110 |  | 70 |  | 26 |  | 46 |  | 8 |  |  |  | 1.9813 | 2.3095
FE ENTITLEMENT FRAMEWORK |  | 271 | 0 | 271 | 257 | 0 | 257 | 94.83% | #DIV/0! | 94.83% | 24 |  | 9 |  | 18 |  | 206 | [9 empty] | 2.6713 | 2.2828
FE & HE OTHER | 54: ESF | 38 | 18 | 56 | 77 | 0 | 77 | 202.6% | 0% | 137.5% |  |  | 77 | [13 empty] | 0.552 | 0.68396
| 60 & 98 |  |  | 0 | 45 | 0 | 45 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  |  | 45 | [11 empty] | 0 | 0.39972
| 70: Skills Intervention | 494 |  | 494 | 0 | 0 | 0 | 0% | #DIV/0! | 0% | [16 empty] | 4.8694 | 0
| 71: Skill Up - Flexible Skills Fund |  |  | 0 | 605 | 0 | 605 | #DIV/0! | #DIV/0! | #DIV/0! | 35 |  |  |  | 345 |  | 165 |  | 20 |  | 20 |  | 20 |  |  |  | 0 | 5.374
TOTAL FE |  | 3755 | 3058 | 6813 | 4564 | 2791 | 7355 | 121.5% | 91.27% | 108% | 1469 | 87 | 513 | 125 | 1280 | 543 | 1302 | 2036 | [8 empty] | 67.1562 | 65.3313
TOTAL HE in FE |  | 932 | 1260 | 2192 | 953 | 1487 | 2440 | 102.3% | 118% | 111.3% | [8 empty] | 448 | 64 | 361 | 1294 | 117 | 129 | 27 | 0 | 21.6067 | 21.6735
GOVMT TRAINING PROGRAMMES | Non - Employed
| 43 & 44 - TfS (L0-3) |  | 159 | 159 | 0 | 32 | 32 | #DIV/0! | 20.13% | 20.13% | [5 empty] | 32 | [10 empty] | 1.5673 | 0.28424
| 42 - Skills for Life and Work (L0-2) | N/A | N/A | N/A | 0 | 100 | 100 | N/A | N/A | N/A |  |  |  | 100 | [12 empty] | N/A | 0.88826
| 97 - Traineeships (L2) | N/A | N/A | N/A | 0 | 134 | 134 | N/A | N/A | N/A | [5 empty] | 134 | [10 empty] | N/A | 1.1903
Employed
| 51: AppsNI (L2 & 3) | 397 | 403 | 800 | 410 | 558 | 968 | 103.3% | 138.5% | 121% |  |  |  |  | 70 | 148 | 340 | 410 | [8 empty] | 7.8857 | 8.5983
| 66 & 69: HLA (L4 & 5) | 181 | 0 | 181 | 229 | 0 | 229 | 126.5% | #DIV/0! | 126.5% | [8 empty] | 10 |  | 219 | [5 empty] | 1.7841 | 2.0341
TOTAL REGULATED AND NON-REGULATED ENROLMENTS |  | 5265 | 4880 | 10145 | 6156 | 5102 | 11258 | 116.9% | 104.5% | 111% | 1469 | 87 | 513 | 225 | 1350 | 857 | 1642 | 2446 | 458 | 64 | 580 | 1294 | 117 | 129 | 27 | 0
NON-REGULATED ONLY |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Essential Skills
Programme |  |  |  |  | TfS Enrols | [8 empty] | FE Enrols | [8 empty] | AppsNI Enrols | [8 empty] | Traineeships Enrols |  |  | Skills for Life and Work Enrols | [8 empty] | 2020/21 Total In-Year Enrolment Activity |  |  |  | 2021/22 Total Planned Enrolment Activity |  |  |  | % of 2020/21 In-Year Enrolment Activity |  |  |  | No. of individuals enrolled on any ES courses
Level |  |  |  |  | EL |  |  | L1 |  |  | L2 |  |  | EL |  |  | L1 |  |  | L2 |  |  | EL |  |  | L1 |  |  | L2 |  |  | L2 |  |  | EL |  |  | L1 |  |  | L2 | [14 empty] | 2020/21 In-Year Individual Activity | 2021/22 Planned Individual Activity | % of 2020/21 In-Year Individual Activity
[5 empty] | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Lit | Num | ICT | Total | Lit | Num | ICT | Total | Lit | Num | ICT | Total | 1377 | 1500 | 108.9%
Age under 16 | 2020/21 In-Year Enrolment Activity | [18 empty] | 1 | [23 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0% | #DIV/0! | #DIV/0! | 0%
2021/22 Planned Enrolment Activity
>=16 and <20 | 2020/21 In-Year Enrolment Activity |  |  |  | 3 | 9 | 0 | 13 | 14 | 29 | 9 | 9 | 3 | 83 | 120 |  | 108 | 199 | 115 | 103 | 162 | 41 | 1 | 3 |  | 3 | 2 | 6 | 1 | 3 | 1 | [12 empty] | 324 | 521 | 195 | 1040 | 391 | 591 | 258 | 1240 | 120.7% | 113.4% | 132.3% | 119.2%
| 2021/22 Planned Enrolment Activity | [12 empty] | 90 | 120 |  | 130 | 240 | 140 | 130 | 190 | 70 |  |  |  | 3 | 3 | 4 | 3 | 3 | 4 | 35 | 35 | 40
Age 20 and over | 2020/21 In-Year Enrolment Activity |  |  |  | 1 |  |  | 2 | 1 | 5 | 1 | 1 |  | 84 | 64 |  | 79 | 115 | 124 | 155 | 204 | 50 |  | 1 |  | 2 |  |  |  |  | 1 | [12 empty] | 324 | 386 | 180 | 890 | 306 | 366 | 188 | 860 | 94.44% | 94.82% | 104.4% | 96.63%
| 2021/22 Planned Enrolment Activity | [12 empty] | 90 | 70 |  | 40 | 80 | 100 | 160 | 200 | 70 |  |  |  | 3 | 3 | 4 | 3 | 3 | 4 | 10 | 10 | 10
[44 empty] | 649 | 907 | 375 | 1931 | 697 | 957 | 446 | 2100 | 107.4% | 105.5% | 118.9% | 108.8%
Programme Totals | 2020/21 In-Year Enrolment Activity |  |  |  | 13 |  |  | 64 |  |  | 23 |  |  | 351 |  |  | 740 |  |  | 716 |  |  | 5 |  |  | 13 |  |  | 6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | EL | L1 | l2 |  | EL | L1 | L2 |  | EL | L1 | L2
| 2021/22 Planned Enrolment Activity |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 370 |  |  | 730 |  |  | 820 |  |  | 0 |  |  | 20 |  |  | 20 |  |  | 140 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 369 | 817 | 745 |  | 370 | 750 | 980 |  | 100.3% | 91.8% | 131.5%
GCSEs
Programme |  |  |  |  | TFS | FE | AppsNI | Trainee-ships | Skills for Life and Work | 2020/21 Total In-Year Activity | 2021/22 Total Planned Activity | % of 2020/21 In-Year Activity
Enrols | PT | 2020/21 In-Year Activity |  |  |  | 481 |  |  |  | 481 | 392 | 81.5%
|  | 2021/22 Planned Activity |  |  |  | 392
| FT | Planned Activity |  |  |  | 36 |  |  |  | 36 | 35 | 97.22%
|  | Actual Activity |  |  |  | 35
Total enrolments | [9 empty] | 517 | 427 | 82.59%
A Level
Programme |  |  |  |  | TFS (43 & 44) | FE | AppsNI (51) | Traineeships (TBD) | Skills for Life and Work | 2020/21 Total In-Year Activity | 2021/22 Total Planned Activity | % of 2020/21 In-Year Activity
Enrols | PT | 2020/21 In-Year Activity |  |  |  | 1376 |  |  |  | 1376 | 1176 | 85.47%
|  | 2021/22 Planned Activity |  |  |  | 1176
| FT | Planned Activity |  |  |  | 375 |  |  |  | 375 | 381 | 101.6%
|  | Actual Activity |  |  |  | 381
Total enrolments | [9 empty] | 1751 | 1557 | 88.92%
RESIDUAL QUALIFICATIONS
ENROLMENT ACTIVITY (EXCLUDING ESSENTIAL SKILLS) |  | 2019/20 enrolments not completed in 2020/21 academic year |  |  | 2021/22 Planned Activity |  |  | % of 2019/20 residual activity planned to be completed | Level 0 |  | Level 1 |  | Level 2 |  | Level 3 |  | Level 4 |  | Level 5 |  | Level 6 |  | Level 7+
|  | Enrolments |  |  | Enrolments |  |  |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments
|  | PT | FT | Total | PT | FT | Total |  | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT
FE MAINSTREAM: 7, 18, 96 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  |  |  | 0 | 2 | 0 | 2 | #DIV/0! |  |  |  |  | 1 |  | 1
HE MAINSTREAM: 7, 18 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  |  |  | 0 | 0 | 0 | 0 | #DIV/0!
FE & HE COST RECOVERY | 45, 46, 58 & 59 |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 80 - NI Prison Service |  |  | 0 | 0 | 0 | 0 | #DIV/0!
FE & HE EMPLOYER LED ACTIVITY - Financial Yr | 48: Bridge to Employment |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 49: Business Improvements Techniques Programme |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 52: Assured Skills |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 62: InnovateUs |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 63: Skills Focus |  |  | 0 | 0 | 0 | 0 | #DIV/0!
FE ENTITLEMENT FRAMEWORK |  |  |  | 0 | 0 | 0 | 0 | #DIV/0!
FE & HE OTHER | 54: ESF |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 60 & 98 |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 70: Skills Intervention |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 71: Skill Up - Flexible Skills Fund |  |  | 0 | 0 | 0 | 0 | #DIV/0!
TOTAL FE |  |  |  | 0 | 2 | 0 | 2 | #DIV/0! | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
TOTAL HE in FE |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GOVMT TRAINING PROGRAMMES | Non - Employed
| 43 & 44 - TfS (L0-3) |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 42 - Skills for Life and Work (L0-2) | N/A | N/A | N/A | 0 | 0 | 0 | N/A
| 97 - Traineeships (L2) | N/A | N/A | N/A | 0 | 0 | 0 | N/A
Employed
| 51: AppsNI (L2 & 3) |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 66 & 69: HLA (L4 & 5) |  |  | 0 | 0 | 0 | 0 | #DIV/0!
TOTAL REGULATED AND NON-REGULATED ENROLMENTS |  | 0 | 0 | 0 | 2 | 0 | 2 | #DIV/0! | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENROLMENT ACTIVITY (EXCLUDING ESSENTIAL SKILLS) |  | 2020/21 enrolments not completed in 2020/21 academic year |  |  | 2021/22 Planned Activity |  |  | % of 2020/21 residual activity planned to be completed | Level 0 |  | Level 1 |  | Level 2 |  | Level 3 |  | Level 4 |  | Level 5 |  | Level 6 |  | Level 7+
|  | Enrolments |  |  | Enrolments |  |  |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments
|  | PT | FT | Total | PT | FT | Total |  | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT
FE MAINSTREAM: 7, 18, 96 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  |  |  | 0 | 0 | 8 | 8 | #DIV/0! | [5 empty] | 6 |  | 2
HE MAINSTREAM: 7, 18 & 99 (Excluding Cost Recovery, Employer Led, Entitlement Framework, Other & Gov Training Programmes) |  |  |  | 0 | 0 | 0 | 0 | #DIV/0!
FE & HE COST RECOVERY | 45, 46, 58 & 59 |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 80 - NI Prison Service |  |  | 0 | 0 | 0 | 0 | #DIV/0!
FE & HE EMPLOYER LED ACTIVITY - Financial Yr | 48: Bridge to Employment |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 49: Business Improvements Techniques Programme |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 52: Assured Skills |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 62: InnovateUs |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 63: Skills Focus |  |  | 0 | 0 | 0 | 0 | #DIV/0!
FE ENTITLEMENT FRAMEWORK |  |  |  | 0 | 0 | 0 | 0 | #DIV/0!
FE & HE OTHER | 54: ESF |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 60 & 98 |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 70: Skills Intervention |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 71: Skill Up - Flexible Skills Fund |  |  | 0 | 0 | 0 | 0 | #DIV/0!
TOTAL FE |  |  |  | 0 | 0 | 8 | 8 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 2
TOTAL HE in FE |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GOVMT TRAINING PROGRAMMES | Non - Employed
| 43 & 44 - TfS (L0-3) |  |  | 0 | 0 | 0 | 0 | #DIV/0!
| 42 - Skills for Life and Work (L0-2) | N/A | N/A | N/A | 0 | 0 | 0 | N/A
| 97 - Traineeships (L2) | N/A | N/A | N/A | 0 | 0 | 0 | N/A
Employed
| 51: AppsNI (L2 & 3) |  |  | 0 | 12 | 10 | 22 | #DIV/0! | [6 empty] | 12 | 10
| 66 & 69: HLA (L4 & 5) |  |  | 0 | 0 | 0 | 0 | #DIV/0!
TOTAL REGULATED AND NON-REGULATED ENROLMENTS |  | 0 | 0 | 0 | 12 | 18 | 30 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 6 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Essential Skills
Level |  |  |  |  | EL | L1 | L2 | Total
2019/20 enrols not completed in 2020/21 academic year | [7 empty] | 0
2020/21 enrols not completed in 2020/21 academic year | [7 empty] | 0
2021/22 Planned Activity | [7 empty] | 0
2021/22 Priority Sector Areas & STEM
Priority Sector Areas and / or 'BROAD' STEM Planned Activity | Agri-Foods (including STEM) |  | Advanced Manufacturing Materials and Engineering (including STEM) |  | Construction and Materials Handling (including STEM) |  | Digital and Creative Technologies (including STEM) |  | Finance Business and Professional Services (including STEM) |  | Life and Health Sciences (including STEM) |  | TOTAL PRIORITY SECTOR AREAS |  | STEM (not already included in Priority Sector Areas) |  | 2020/21 IN-YEAR TOTAL PRIORITY SECTOR AREAS +/ OR STEM ACTIVITY |  | 2021/22 PLANNED TOTAL PRIORITY SECTOR AREAS + / OR STEM |  | % OF 2020/21 IN-YEAR ACTIVITY PRIORITY SECTOR AREAS + / OR STEM ACTIVITY ACHIEVED
| Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments |  | Enrolments
| PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT
L0-1 | 0 | 0 | 71 | 8 | 36 | 10 | 285 | 10 | 642 | 0 | 0 | 0 | 1034 | 28 | 19 |  | 1139 | 18 | 1053 | 28 | 92.45% | 155.6%
L2 | 313 | 0 | 209 | 99 | 0 | 157 | 470 | 157 | 1933 | 71 | 52 | 37 | 2977 | 521 | 21 |  | 3336 | 546 | 2998 | 521 | 89.87% | 95.42%
L3 | 0 | 0 | 460 | 281 | 98 | 164 | 98 | 164 | 1051 | 523 | 263 | 100 | 1970 | 1232 |  | 30 | 2522 | 1535 | 1970 | 1262 | 78.11% | 82.21%
L4 + | 0 | 0 | 248 | 61 | 83 | 70 | 28 | 70 | 674 | 485 | 0 | 76 | 1033 | 762 |  |  | 938 | 933 | 1033 | 762 | 110.1% | 81.67%
Totals | 313 | 0 | 988 | 449 | 217 | 401 | 881 | 401 | 4300 | 1079 | 315 | 213 | 7014 | 2543 | 40 | 30 | 7935 | 3032 | 7054 | 2573 | 88.9% | 84.86%
| 313 |  | 1437 |  | 618 |  | 1282 |  | 5379 |  | 528 |  | 9557 |  | 70 |  | 10967 |  | 9627
% Provision | 1.678% |  | 7.706% |  | 3.314% |  | 6.875% |  | 28.84% |  | 2.831% |  | 51.25% |  | 0.3754% |  | 59.4% |  | 51.62%
Priority Sector Areas and / or 'BROAD' STEM Planned Activity | Agri-Foods (including STEM) |  | Advanced Manufacturing Materials and Engineering (including STEM) |  | Construction and Materials Handling (including STEM) |  | Digital and Creative Technologies (including STEM) |  | Finance Business and Professional Services (including STEM) |  | Life and Health Sciences (including STEM) |  | TOTAL PRIORITY SECTOR AREAS |  | STEM (not already included in Priority Sector Areas) |  | 2020/21 IN-YEAR TOTAL PRIORITY SECTOR AREAS +/ OR STEM ACTIVITY |  | 2021/22 PLANNED TOTAL PRIORITY SECTOR AREAS + / OR STEM |  | % OF 2020/21 IN-YEAR ACTIVITY PRIORITY SECTOR AREAS + / OR STEM ACTIVITY ACHIEVED
| Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals |  | Individuals
| PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT | PT | FT
L0-1 | 0 | 0 | 6 | 8 | 3 | 10 | 25 | 10 | 56 | 0 | 0 | 0 | 90 | 28 | 19 |  | 109 | 18 | 109 | 28 | 100% | 155.6%
L2 | 55 | 0 | 37 | 99 | 0 | 157 | 84 | 157 | 345 | 71 | 9 | 37 | 530 | 521 | 21 |  | 551 | 546 | 551 | 521 | 100% | 95.42%
L3 | 0 | 0 | 336 | 281 | 72 | 164 | 72 | 164 | 770 | 523 | 192 | 100 | 1442 | 1232 |  | 30 | 1442 | 1535 | 1442 | 1262 | 100% | 82.21%
L4 + | 0 | 0 | 270 | 61 | 90 | 70 | 30 | 70 | 736 | 485 | 0 | 76 | 1126 | 762 |  |  | 1126 | 933 | 1126 | 762 | 100% | 81.67%
Totals | 55 | 0 | 649 | 449 | 165 | 401 | 211 | 401 | 1907 | 1079 | 201 | 213 | 3188 | 2543 | 40 | 30 | 3228 | 3032 | 3228 | 2573 | 100% | 84.86%
| 55 |  | 1098 |  | 566 |  | 612 |  | 2986 |  | 414 |  | 5731 |  | 70 |  | 6260 |  | 5801
% Provision | 0.4885% |  | 9.753% |  | 5.028% |  | 5.436% |  | 26.52% |  | 3.677% |  | 50.91% |  | 0.6218% |  | 61.71% |  | 51.53%