# College Development Plan July 2023 Progress Report Summary

## College Development Plan Progress Report July 2023

Our 2022/23 College Development Plan (CDP) was submitted to our partner organisation, the Department for the Economy (DfE), in August 2022 and approved in December 2022.

The CDP is a mandatory annual plan that sets out our agreed targets in relation to:

- Qualifications

- Employers

- Social Inclusion

We  formally report on the CDP to the Department three times  a year ,in July, November and March, and monitor progress regularly throughout.  Our July 2023 position is summarised in Appendix 1.  Performance is colour coded as follows:

On Track/Achieved/Completed

Slippages/Areas being Monitored

Not likely to be met/Not Met/Not Achieved

Not yet started/Reported/Data not Available

# Appendix 1: College Development Plan July 2023 Progress Report

# CDP Progress Report July 2023

July 2023 Progress against Planned Activity

|  | Target (2022/23) | Actual (July 2023) |
| --- | --- | --- |
| Qualifications | Deliver 16,211 Level 0-3 FE Mainstream qualification enrols. | 17,555 Level 0-3 FE Mainstream qualification enrols. |
|  | Deliver 2,465 HE (Levels 4, 5, 6) enrols. | 2,256 HE (Levels 4, 5, 6) enrols. We exceeded our part time HE enrolment target; however, we did not meet our full-time HE enrolment targets. |
|  | Work with businesses to deliver: |  |
|  | 226 Traineeships | 201 Traineeships Early withdrawals and early positive progression to Apprenticeships reduced our number of full-time traineeship enrolments. |
|  | 687 Apprenticeships | 803 Apprenticeships |
|  | 263 HLAs | 317 HLAs |
|  | Deliver 2,300 Essential Skills qualification enrols. | 2,261 Essential Skills qualification enrols. |
|  | Deliver PSSA to 7,950 individual learners | Delivered PSSA to 8,351 individual learners |
| Employers | Deliver £290k of InnovateUs projects. | £291, 800 We have delivered 85 projects to date, exceeding our target of 76 projects. |
|  | Deliver £275k of Skills Focus training with employers. | £283,972 |
|  | Deliver 16 Assured Skills Academies and 4 NICS Academies. | 15 Academies 4 NICS Academies |
|  | Engage 12 companies in the Innovation Voucher scheme. | 12 |
| Social Inclusion | Enrol 9,764 learners from the most deprived quintiles. | 9,869 |
|  | Enrol 3,037 learners declaring a disability or long-term health problem. | 4,162 |
|  | Deliver 5,826 enrolments on Entry Level and Level 1 programmes (including Essential Skills). | 6,857 |
|  | Deliver programmes targeting 729 long-term unemployed. | 1,082 |
|  | Deliver 1,816 ESOL enrols. | 2,267 |
|  | Register 761 prisoners for accredited qualifications. | 1,170 |